## Sheet1
Product Backlog
ID | Item | Owner | Priority | Effort | Status | Definition of Done
C1 | As a user i want to be able to check the current date so i can know the current date | Product Owner | 2 | 2 | Done | When the user is able to check the current date
C2 | As a user i want to be able to check the current month so i can be know the current month | Product Owner | 2 | 2 | Done | When the user is able to check the current month
C3 | As a user i want to be able to check how many days are in the month so i can know how many days are there in the current month | Product Owner | 1 | 1 | Done | When the user is able to see all the days in a given month
C4 | As a user i want to be able to update the calender with my own events so i can keep up to date with my events | Product Owner | 1 | 4 | Not Started | When the user is able to add events to calendar dates
C5 | As a user i want to be able to check my event timings so i can be up to date and plan | Product Owner | 1 | 3 | Not Started | When the user is able to see the time of their event on the calendar
C6 | As a user i want to be able to check the location of my events so i can go to the right event location | Product Owner | 1 | 2 | Not Started | When the user is able to see the location of their event on the calendar
C7 | As a user i want to be able to search for my event on the calender so i can know when and where is the event | Product Owner | 1 | 7 | Not Started | When the user is able to use a search feature to filter events on their calendar (by event title)
C8 | As a user i want to view the calendar in month format to visualise what I am doing this month | Product Owner | 1 | 1 | Done | When the user is presented with a view that is a single month, columned by days of the week
C9 | As a user i want to be able to switch to the next month view to check the next month's events | Product Owner | 1 | 2 | In Progress | When the user is able to shift their view from a given month to another (Start with the adjacent ones only)
E1 | As an event planner i want to create an event to plan my event | Product Owner | 1 | 3 | Not Started | When the user is able to create an event (subsequent UI for it)
E2 | As an event planner i want to set my event's time so people know when it is | Product Owner | 1 | 2 | Not Started | When the user is able to set the time for their event
E3 | As an event planner i want to set my event's location so people know where it is | Product Owner | 1 | 2 | Not Started | When the user is able to enter the events location
E4 | As an event attendee i want to be able to register for an event so people know i am going | Product Owner | 2 | 3 | Not Started | When a user is able to click a button to register for an event, and they are added to a collection of attendees
E5 | As a user i want to be able to make an account to create/register for events | Product Owner | 1 | 2 | Not Started | When the user is able to create an entity for their account information
E6 | As a user i want to be able to set my account details so people know who i am and how to contact me | Product Owner | 1 | 3 | Not Started | When the user is able to set the fields of their account (Account information)
E7 | As a user i want to be able to search for events via parameters (Title, location, date) so I can discover any events that peak my interest that im able to go to | Product Owner | 3 | 8 | Not Started | When the user is able to search for events based on paramenters (E.g. name or location or date/time)
E8 | As an event planner i want to write a description about my event so that people know what it is about | Product Owner | 2 | 1 | Not Started | When the user is able to write a description for the event that will be present on their event's window/page
E9 | As an event attendee i want all the events sorted based on date so that i can organize my time for important upcoming event | Product Owner | 4 | 5 | Not Started | When users are able to sort their "attending events" in order of time
E10 | As an event planner i want my event to indicate when its sold out so people know that it is full | Product Owner | 2 | 5 | Not Started | When a user's event's register button is unclickable when its full (Visually clear that its sold out/full)
E11 | As an event planner i want to set how many people can attend my event (if theres a cap) so that my event doesnt go over capacity | Product Owner | 2 | 3 | Not Started | When the user is able to set a limit to their event that will prevent users from registering when the limit is reached