## Sheet1
Story Points
Scrum Meeting | Story points Planned (1 pts = 1 hour) | Story Points Completed (1 pts = 1 hour)
1 | 20 | 11
2 | 40 | 13
3 | 60 | 15
4 | 80 | 16
Story Points
Scrum Meeting | Story points Planned (1 pts = 1 hour) | Story Points Completed (1 pts = 1 hour)
0 | 80 | 80
1 | 60 | 69
2 | 40 | 56
3 | 20 | 41
4 | 0 | 25